# STATEMENT OF WORK

# For the MSBA Team’s Business Analytics

# Applied Learning Experience with

Emerald Transformer

Market Opportunity Analysis

10/28/2025

Revised 01/10/2026

Prepared By:

Mary Osborne and Robert Mee

Summary

This Statement of Work (“SOW”) is by and between the University of Tennessee Masters in Business Analytics (MSBA) program and Emerald Transformer and sets forth the terms and conditions that will govern the 15-week project during the Spring Semester 2026 as further set forth below. The MSBA program desires to provide for four of its students an applied learning experience to develop innovative value-creation skills. The project involves identifying expansion opportunities for Emerald.

The three-credit-hour class will be supported by Mary Osborne (Client Partner) and Adam Petrie (UT Faculty Partner).

This Statement of Work will guide and measure this project to the mutual satisfaction of Emerald Transformer, the students, and the MSBA program.

# Project Team

| UT MSBA Students |  | Email |
| --- | --- | --- |
| David Patrick Mullaly | (Project Manager) | dmullaly@vols.utk.edu |
| Afia Adiba |  | aadiba@vols.utk.edu |
| Jazmin Elias |  | jelias1@vols.utk.edu |
| Lauren Milsom |  | lmilsom@vols.utk.edu |

Partners

| Name | Email | Phone |
| --- | --- | --- |
| Mary Osborne (Project Lead) | mosborne@emeraldtransformer.com | (m) |
| Stuart Prior (Sponsor) | sprior@emeraldtransformer.com |  |
| Adam Petrie (UT Faculty) | apetrie@utk.edu | (m) |

# Duration of Engagement

The project will last for fifteen weeks, from January 20, 2026 until approximately May 8, 2026.

Project Description

Emerald Transformer has multiple locations throughout the US that specialize in different services for distribution electrical equipment (the U.S. Grid). We have three main customer targets segregated by size: investor-owned utilities (IOUs), cooperatives, municipalities. We are a national company with 8 locations, with plans for geographic expansion, product line expansion, organic growth and increased market share. The three main regions we would like to explore are the Northeast, West, and Pacific Northwest. This exploration should include the density of the target customers in that area and the competitive landscape.

.

Data Description

We will provide all current customer information including locations, volume, and footprint. All data will be in Excel format.

Objective

Determine the most opportune areas and product lines for sustained and profitable growth.

Deliverable

Presentation and report on full market opportunity analysis for future growth plans.

Tentative Project Timeline

| # Phase | # Weeks | # Deliverable |
| --- | --- | --- |
| # One | # 1-2 | # Become acquainted with data and project objectives |
| # Two | # 3-7 | Milestone 1 |
| # Three | # 8-12 | Milestone 2 |
| # Four | # 13-14 | Preparing final report and presentation |
| # Five | # 15 | # Milestone 3 – Final report and presentation of results – May 7 or 8 |

### Student Evaluation Criteria

# Depth of understanding of business problem / objective.

# Usefulness of the team’s analysis and recommendations.

# Adherence to project schedules and requirements, and successful completion of project deliverables.

- Professionalism, ability to communicate with all stakeholders, quality of project reports and presentations.

- Team input on individual team members’ contributions.

# Reporting and Meetings

To launch the project, the first meeting between representatives and UT faculty and students will take place via videoconference on January 23, 2026. Thereafter, the team, partners, and faculty will hold weekly conference calls or videoconferences at a regularly scheduled time. In addition, the MSBA Project Manager will provide regular email status reports on the team’s progress to the stakeholders. The final project presentation will be held in person at UTK (with videoconference link), preferably on May 7 or 8, 2026.

Travel Costs

The company will cover all travel expenses, including those incurred by UT students traveling to the company site (if needed) and any company representatives traveling to UTK for the final presentation.